## NEW Cost Summary
Ref | Item | CONTRACT SUM | CERTIFIED PAYMENTS TO CONTRACTOR | ACCRUED & ANTICIPATED PAYMENTS | TOTAL FORECAST EXPENDITURE | VARIANCE - TOTAL | VARIANCE - IN PERIOD
1 | CONTRACT SECTION
1.1 | CONTRACT | 0 | 0
1.2 | PROVISIONAL SUMS ADJUSTMENTS (PSA) | 0
1.3 | VALUE ENGINEERING |  | 0
1.4 | EMPLOYERS AGENT INSTRUCTIONS (EAI) |  | 0
1.5 | CONTRACTORS VARIATION REQUESTS (CVR) |  | 0
1.6 | EXTENSION OF TIME (EOT) |  | 0
1.7 | DAMAGES DEDUCTED (DD) |  | 0
1.8 | RISK REGISTER (RR) |  | 0
1.9 | RETENTION |  | 0
Note on C2: Patrick King: This value is populated by Total value of messuared works on the NEW Contract Sum Tab
Note on D2: Patrick King: The field is populated by the messured works total CERTIFIED PAYMENTS TO CONTRACTOR
Note on C3: Patrick King: This value is populated by Total value of messuared works on the NEW Contract Sum Tab
Note on D3: Patrick King: The field is populated by the messured works total CERTIFIED PAYMENTS TO CONTRACTOR
Note on C4: Patrick King: This value is populates by total value of Provisional Sums on the NEW Contract SUM TAB (C12) Field
Note on B5: Patrick King: All this data is linked fron the NEW EA Change Tab
Note on B6: Patrick King: Patrick King: All this data is linked fron the NEW EA Change Tab
Note on B7: Patrick King: Patrick King: All this data is linked fron the NEW EA Change Tab
Note on B8: Patrick King: Patrick King: All this data is linked fron the NEW EA Change Tab
Note on B9: Patrick King: Patrick King: All this data is linked fron the NEW EA Change Tab
Note on B10: Patrick King: Patrick King: All this data is linked fron the NEW EA Change Tab
Note on B11: Patrick King: Patrick King: All this data is linked fron the NEW EA Change Tab

## NEW Contract Sum
Ref | Item | CONTRACT SUM | CERTIFIED PAYMENTS TO CONTRACTOR | ACCRUED & ANTICIPATED PAYMENTS | TOTAL FORECAST EXPENDITURE
1 | Measured works
1.1 | Windows & Doors - Replace Spandrel Panels | 70271.56 | 70271.56 | 0 | 70271.56
1.2 | Services - Holes in spandrel panels & firestopping | 12600 | 12600 | 0 | 12600
1.3 | Preliminaries | 23856 | 23856 | 0 | 23856
1.4 | Scaffolding & Temporary Works | 49185.5 | 49185.5 | 0 | 49185.5
1.5 | Main contractor design fees | 5490 | 5000 | 0 | 5000
2 | Provisional Sums
2.1 | Provisional Sums | 5000 | 5000 | 0 | 5000

## NEW EAChange
Ref | Item | CONTRACT SUM | CERTIFIED PAYMENTS TO CONTRACTOR | ACCRUED & ANTICIPATED PAYMENTS | TOTAL FORECAST EXPENDITURE | VARIANCE - TOTAL | VARIANCE - IN PERIOD
1 | EMPLOYERS AGENTS INSTRUCTIONS
1.1 | Pre-commencement extra works; for KT heating, additional time. | 0 | 4270 | 0 | 4270 | 4270 | 4270
1.2 | Wentworth Mews Mastic Repair | 0 | 1797 | 0 | 1797 | 1797 | 1797
1.3 | Proforma Payment to Cadent Gas | 0 | 63448.352 | 0 | 63448.352 | 63448.352 | 63448.352
1.4 | Omit; Building control submission & fees (completed by ECDA ) | 0 | -2500 | 0 | -2500 | -2500 | -2500
1.5 | Additional one week for scaffold to complete mastic repairs. | 0 | 4806.2 | 0 | 4806.2 | 4806.2 | 4806.2
1.6 | Welfare and Container Hire (06/02 - 17/03) | 0 | 2033.05 |  | 2033.05 | 2033.05 | 2033.05
1.7 | Welfare and Container Hire (18/03 - 19/05) | 0 | 3285 |  | 3285 | 3285 | 3285
1.8 | Welfare and Container Hire (20/05 - 24/06) | 0 | 1095 | 0 | 1095 | 1095 | 1095
1.9 | Cadent Gas Design work as per TWC letter dated 02/03/23 | 0 | 6636.96 | 0 | 6636.96 | 6636.96 | 6636.96
1.1 | Omit: Prelims item Resident Liaison Officer (£7992) | 0 | -7992 |  | -7992 | -7992 | -7992
[6 empty] | 76879.562 | 76879.562
2 | ADJUSTMENT OF PROVISIONAL SUMS
2.1 | Item 01 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Item 02 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Item 03 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Item 04 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Item 05 | 0 | 0 | 0 | 0 | 0 | 0
2.6 | Item 06 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
3 | VALUE ENGINEERING
3.1 | Item 01 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Item 02 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Item 03 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
4 | CONTRACTORS VARIATION REQUEST
4.1 | Item 01 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Item 02 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Item 03 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
5 | EXTENSION OF TIME
5.1 | Item 01 | 0 | 0 | 0 | 0 | 0 | 0
5.2 | Item 02 | 0 | 0 | 0 | 0 | 0 | 0
5.3 | Item 03 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0

## New Cost Reporting
Interim Payments | Month | Forecast Monthly | Actual Monthly | Forecast Cumulative | Actual Cumulative
1 | 2022-11-01 | 25000 | 46900.7685 | 25000 | 46900.7685
2 | 2022-12-01 | 38352 | 13283.2895 | 63352 | 60184.058
3 | 2023-01-01 | 25000 | 102975.33 | 88352 | 163159.388
4 | 2023-02-01 | 35000 | 37134.44 | 123352 | 200293.828
5 | 2023-05-01 | 25000 | 13213.51 | 148352 | 213507.338
6 | 2023-06-01 | 13891 | 18818.21 | 162243 | 232325.548
8 | 2024-07-01 | #REF! | #REF! | #REF! | #REF!